## Sheet1
S.No. | Date | Task | Time Stamp
1 | 22/07/2022 | Taking moralis API IN THE NEXT.js File as the API key used in the template expired. Made the connection of our project with Moralis API | 8am-9pm 12hours
2 | 23/07/2022 | Making the Connection of our app to the ethereum node and Non-Custodail wallet. Used use effect hooks for the connection reloading and renegaration engine support | 7am-4pm 8 hours
3 | 24/07/2022 | Making the Smart contract for the NFT Marketplace and compiling it and deploying to testnet rinkeby, testing the smart contract functions. | 10am-8pm 9hours
4 | 25/07/2022 | Using the Mint function fir ERC-721 and exporting the meta-data to the IPFS servers with the help of infura node services | 8am-6:30pm 9.5 hours
5 | 26/07/2022 | Fetching the nfts and meta data asssociated with it at the home page and integrating with the infura IPFS node to fetch the NFTs and integrating it with the buy functionality(Transfering ownership of the NFT token) with the user(client) | 8am-9pm 12hours (completion day)